## Slide 2: WAGNER FORD road BRIDGE REHABILITATION moT-cr218-1.00

## Slide 3: PROJECT LOCATION
N
PROJECT LOCATION
CSX RR
WAGNER FORD ROAD

## Slide 4: Project Scope
Rehabilitate spalled abutment concrete
Replace expansion joints, add pedestrian fence, seal bridge deck
Replace approach guardrail

## Slide 5: Existing Conditions
Looking south along CSX mainline tracks
Spalled concrete on East abutment

## Slide 6: MEASUREMeNT AND TESTING
Abutment corrosion mapping, sampling, and testing

## Slide 7: Impacted Properties
N

## Slide 8: Impacted Properties
N

## Slide 9: Impacted Properties
N

## Slide 10: Impacted Properties
N

## Slide 11: Impacted Properties
N

## Slide 12: Impacted Properties
N

## Slide 13
NORTH
EXISTING RIGHT-OF-WAY

## Slide 14
NORTH
Rumpke waste, Inc.
Contractor access to West abutment will be made from within existing Right of Way; no property acquisition required
Rumpke Dayton Office
End of Public Service Road

## Slide 15
NORTH
City of Dayton
Temporary easement required to access East abutment work zone (thru CSX easement) from Dayton Park Drive
CSX Needmore Yard
Dayton Park Drive

## Slide 16
NORTH
CSX Transportation
Temporary easement required to access East abutment work zone from Dayton Park Drive
CSX Needmore Yard
Dayton Park Drive

## Slide 17: Rumpke Parcel

## Slide 18: City of Dayton Parcel

## Slide 19: CSX Parcel

## Slide 20: PROJECT COSTS
Design Engineering $250,000
Right-of-Way TBD by appraisal
Construction $1,000,000
Construction Inspection by MCEO
CSX Review and Force Account $50,000
Total Project Cost $1,300,000 + ROW

## Slide 21: PROJECT SCHEDULE
Final Design Engineering: thru October 2023
Right-of-Way Acquisition: June 2023 – Nov. 2023
Advertise, Sale & Award: Nov. 2023 – Jan. 2024
Construction: 180 calendar days

## Slide 22: Questions?