## RW Acquisition
MOT-DIA Northeast Logistics Access Project
PID 115795
Montgomery County Engineers Office
Right of Way Acquisition Gantt Chart
Estimated No. Parcels | 45
| Start | End | 2023 |  |  |  |  | 2024 | [11 empty] | 2025 | [11 empty] | 2026
Task/ Milestone |  |  | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
NEPA Approval |  | 2024-03-01
Stage 2 Plan Submittal |  | 2024-08-23
Preliminary R/W Plan Submittal |  | 2024-08-23
Final R/W Plan Submittal |  | 2024-12-20
Final R/W Plan Approval |  | 2025-01-31
R/W Authorization |  | 2025-02-28
R/W Acquisition Complete |  | 2026-08-14
Procure R/W Consultant | 2023-09-01 | 2024-02-01
Develop Scope/RFP
Advertise
Select Consultant
Develop Price Proposal
Negotiate
Award/NTP
Preliminary R/W Tasks | 2024-03-01 | 2025-02-28
Title Reports
Appraisals
Appraisal Reviews
Final R/W Tasks | 2025-03-01 | 2026-08-14
Negotiations
Closings
Recordings
District R/W Certification |  | 2026-08-21
Sale |  | 2026-11-04
Award |  | 2026-12-08
Construction | 2027-03-01 | 2028-09-01